## Cover Page
Project | iRevatureQuizPro
Description | This project is a iOS Mobile App which enables trainers, ambassadors and associates to configure/access the quiz
Team | iOS USF Batch - JAN 2020
Start Date | 2020-03-02
Project Type | P3 Project
Author | Udayakumar Mathivanan

## Course & Quiz Management
User Story | Category | Story Points | Priority | Order
Login Page - Users (Trainer, Associates , Ambassdor) | Login |  | High | 1
As a user I should be able to change the password at given point of time. | Login |  | Medium | 8
As a revature ambassdor I should be able to setup an event | Event |  | Low
As a trainer I should be able to create a course from my iOS Mobile Device | Course |  | Low
As a trainer I should be able to view all the courses I have created from my iOS Mobile Device | Course |  | Low
As a trainer I should be able to modify the course I have created from my iOS Mobile Device | Course |  | Low
As a trainer I should be able to delete the course I had created which are in Draft Mode | Course |  | Low
As a trainer I should be able to create a quiz from the existing questions category | Quiz |  | High | 4
As a trainer I should be able to see all the quizzes I had created | Quiz |  | High | 4
As a revature ambassdor I should be able to attach a quiz to an event code (sent from Marketo) | Event |  | High | 2
As a trainer I should be able to attach a quiz to a batch/student/course | Quiz |  | Medium | 5
As a trainer I should be able to delete all the quizzes I had created and in Draft mode | Quiz |  | Medium | 6
As a trainer I should be able to see the quiz results by Batch/Student/Question | Quiz |  | High | 5
As a Associate I should be able to see all the quiz assigned to me | Quiz |  | High | 5
As a Associate I should be able to take up a quiz on at any point of time within 15 mins from actual quiz time | Quiz |  | High | 5
As a Associate I should be able to see the results of the quiz I had taken so far | Quiz |  | Medium | 6
As a event Attendee I should be able to enter into an event and takeup quiz | Event |  | High | 7
As a revature ambassdor I should be able to see the results of the quiz by attendee | Event |  | High | 3
As a Trainer I should be able to import questions | Quiz |  | High | 4
Total User Stories (High & Medium) | 14
Total User Stories (Low) | 5

## Sprint Plan
Sprint # | Start Date | End Date | Story Points for Each Sprint | Velocity | Actual | QA Build
Sprint 1 | 2020-03-02 | 2020-03-06 |  | 240 | 236
Sprint 2 | 2020-03-09 | 2020-03-13 |  | 240 | 204
Sprint 3 | 2020-03-16 | 2020-03-19 |  | 240 | 144
|  |  | Total | 720 | 584
|  | P3 Showcase | 19th March
|  | Promotional Cermony | 20th March
|  | Staging | 23rd March

## Project Resources
UI Wireframes | Proto | Team | Sprint 0
High Level Design | Client App Architecture , Server Architecture | Team,Uday
LLD | Class Design, DB Design (Local Device) | Team
API Specification | Mock API Spec | Uday
Production API | RevPro Dev Environment - Hosted on GCP Cloud | Uday
Project Plan | Microsoft Project Plan | Uday
DSM MOM |  | CSM - 3 days rotation policy | Nathan

## Tasks - Owners
Resources | Owner | Database | Library | Tool | Endpoint Url | Due Date
DB Design | Nathan | SQLite | EasySQL |  |  | 2020-03-05
UI Wireframes | Wes Otero |  |  | Proto.io |  | 2020-03-05
LLD - Class Diagram | Kjay |  |  | Gliffy , Visual Pardigm , Creatively |  | 2020-03-05
LLD - Activity Diagram | Jeremy |  |  | Gliffy , Visual Pardigm , Creatively |  | 2020-03-05
API Specifiation | Uday |  |  | Swagger |  | 2020-03-04
API - Mock Test | Kyle |  |  | Postman, JSON Validation |  | 04-Mar - 2pm (Uday) - 05th Mar
API - Production (Dev) | Uday |  |  |  |  | 2020-03-09
Project Structure - Push to GitHub | Mark |  |  | Xcode/Git |  | 2020-03-04
SQL Library - Framework | Mark

## Technology Stack
Technology | Version | License | Reference